## Tasks
ID | Task Name | Duration | Start | Finish | % Complete | Resource Names | Predecessors | Priority | Notes
1 | VGT Actuator Development | 120 | 6/1/2025 | 11/15/2025 | 15 |  |  | 500 | Variable geometry turbo actuator project
2 | Concept Design Phase | 30 | 6/1/2025 | 7/10/2025 | 45 |  |  | 800
3 | Mechanism Kinematic Study | 15 | 6/1/2025 | 6/20/2025 | 80 | Sarah Chen;Mike Torres |  | 800 | Linkage geometry optimization
4 | Motor Selection Analysis | 10 | 6/5/2025 | 6/18/2025 | 75 | Mike Torres |  | 700 | Evaluate brushless DC options
5 | Position Sensor Selection | 8 | 6/10/2025 | 6/20/2025 | 60 | Jake Morrison | 4 | 700 | Hall effect vs optical encoders
6 | Concept Design Review | 0 | 6/25/2025 | 6/25/2025 | 0 | Sarah Chen;Management | 3;4;5 | 1000 | Gate review for funding approval
7 | Detailed Design Phase | 35 | 6/26/2025 | 8/15/2025 | 30 |  |  | 800
8 | Housing Design - Cast Aluminum | 20 | 6/26/2025 | 7/22/2025 | 50 | Sarah Chen | 6 | 800 | Thermal analysis required
9 | Gear Train Design | 18 | 6/28/2025 | 7/24/2025 | 45 | Mike Torres | 6 | 900 | Need backlash analysis
10 | Control Electronics PCB | 25 | 7/1/2025 | 8/5/2025 | 35 | Jake Morrison | 5;6 | 800 | EMI compliance required
11 | Position Feedback Algorithm | 15 | 7/10/2025 | 7/30/2025 | 40 | Dr. Kim Park | 5 | 700 | PID tuning parameters
12 | Thermal Management Design | 12 | 7/15/2025 | 7/31/2025 | 25 | Sarah Chen | 8 | 700 | Must survive 200C exhaust temps
13 | Design Review - Detailed | 0 | 8/15/2025 | 8/15/2025 | 0 | Sarah Chen;Management | 8;9;10 | 1000 | Final design approval gate
14 | Prototype Build | 25 | 8/18/2025 | 9/22/2025 | 10 |  |  | 900
15 | Order Long-Lead Components | 20 | 8/18/2025 | 9/15/2025 | 15 | Procurement | 13 | 900 | Motors have 8 week lead time
16 | PCB Fabrication | 15 | 8/20/2025 | 9/10/2025 | 10 | External PCB Fab | 13 | 800 | 4-layer board
17 | Housing Casting | 30 | 8/22/2025 | 10/2/2025 | 5 | Acme Casting | 13 | 900 | First article inspection required
18 | CNC Machining - Housing | 8 | 10/3/2025 | 10/14/2025 | 0 | Machine Shop | 17 | 800
19 | Gear Manufacture | 12 | 9/5/2025 | 9/22/2025 | 0 | Gear Supplier | 13 | 900 | Hobbed gears - case hardened
20 | PCB Assembly & Test | 5 | 9/12/2025 | 9/18/2025 | 0 | Electronics Lab | 16 | 800 | Functional test after assembly
21 | Prototype Assembly | 6 | 10/15/2025 | 10/22/2025 | 0 | Mike Torres;Assembly | 18;19;20 | 1000
22 | Initial Function Test | 0 | 10/23/2025 | 10/23/2025 | 0 | Mike Torres | 21 | 1000 | Verify basic operation
23 | Test & Validation | 30 | 10/24/2025 | 12/5/2025 | 0 |  |  | 900
24 | Position Accuracy Test | 5 | 10/24/2025 | 10/30/2025 | 0 | Lab Team | 22 | 800 | +/- 1 degree accuracy target
25 | Response Time Test | 4 | 10/31/2025 | 11/5/2025 | 0 | Lab Team | 24 | 800 | Must respond within 200ms
26 | Temperature Cycling | 10 | 11/6/2025 | 11/19/2025 | 0 | Lab Team | 25 | 900 | -40C to 200C cycling
27 | Durability Test - 100k cycles | 15 | 11/10/2025 | 11/28/2025 | 0 | Lab Team | 22 | 1000 | Life target validation
28 | Vibration Testing | 5 | 11/20/2025 | 11/26/2025 | 0 | Lab Team | 22 | 800 | ISO 16750-3 automotive standard
29 | EMI Compliance Test | 4 | 11/25/2025 | 11/30/2025 | 0 | EMI Lab | 20 | 900 | CISPR 25 automotive EMI
30 | Test Report Complete | 0 | 12/5/2025 | 12/5/2025 | 0 | Engineering | 24;25;26;27;28;29 | 1000 | Summarize all test results
31 | Production Release | 0 | 12/10/2025 | 12/10/2025 | 0 | Management | 30 | 1000 | Release to manufacturing